# SCRUM Development Process by Ken Schwaber

### Roles

Management: Led by the Product Manager, it defines initial content and timing of the
release, then manages their evolution as the project progresses and variables change.
Management deals with backlog, risk, and release content.

Development teams: Development teams are small, with each containing developers,
documenters and quality control staff. One or more teams of between three and six
people each are used. Each is assigned a set of packets (or objects), including all backlog
items related to each packet. The team defines changes required to implement the
backlog item in the packets, and manages all problems regarding the changes. Teams can
be either functionally derived (assigned those packets that address specific sets of product
functionality) or system derived (assigned unique layers of the system). The members of
each team are selected based on their knowledge and expertise regarding sets of packets,
or domain expertise.

### Meetings

All teams meeting to present work and review progress, raising and
resolving issues and problems, adding new backlog items. Risk is reviewed and
appropriate responses defined.
Characteristics:
- The whole team and product management are present and participate.
- The review can include customers, sales, marketing and others.
- Review covers functional, executable systems that encompass the objects assigned to
that team and include the changes made to implement the backlog items.
The way backlog items are implemented by changes may be changed based on the
review.
New backlog items may be introduced and assigned to teams as part of the review,
changing the content and direction of deliverables.
The time of the next review is determined based on progress and complexity. The
Sprints usually have a duration of 1 to 4 weeks.

### Process Model:

Flexible deliverable - the content of the deliverable is dictated by the environment.
- Flexible schedule - the deliverable may be required sooner or later than initially planned.
- Small teams - each team has no more than 6 members. There may be multiple teams
within a project.
- Frequent reviews - team progress is reviewed as frequently as environmental
- complexity and risk dictates (usually 1 to 4 week cycles). A functional executable
must be prepared by each team for each review.
- Collaboration - intra and inter-collaboration is expected during the project.
- Object Oriented - each team will address a set of related objects, with clear interfaces
and behavior.

### Artifacts

Many artifacts are created while building the system. Artifacts may be used to guide
thinking, check completeness, and create an audit trail. The artifacts consist of
documents, models, programs, test cases, and other deliverables created prior to creating
the implemented system. When available, a metamodel defines the semantic content of
model artifacts. Notation describes the graphing and documentation conventions that are
used to build the models.